## Sheet1
Stage | Task | Duration (days) | Start Date | End Date | What to Learn | Tips
1.1: Flask Environment Setup | Set up Python virtual environment, install Flask | 3 | 2024-08-24 | 2024-08-26 | Learn about virtual environments, Flask basics, and environment management. | Familiarize yourself with `venv` or `virtualenv`, understand Flask's structure and components.
1.2: Database Setup | Design schema, set up SQLAlchemy, create migrations | 3 | 2024-08-27 | 2024-08-29 | Understand relational databases, ORM (Object-Relational Mapping) with SQLAlchemy, and migration tools like Flask-Migrate. | Practice designing database schemas, get comfortable with writing migrations, and querying with SQLAlchemy.
1.3: Implement CRUD Operations | Implement Create, Read, Update, Delete operations | 7 | 2024-08-30 | 2024-09-06 | Learn how to handle HTTP requests, forms, and perform database operations using SQLAlchemy. | Build small CRUD examples, focus on understanding Flask routes and how they interact with the database.
1.4: Version Control with Git | Initialize Git, create branches, push to GitHub | 3 | 2024-09-07 | 2024-09-09 | Understand Git basics, branching, merging, and how to use GitHub for version control. | Learn the common Git commands, practice working with branches, and creating pull requests.
2.1: Writing Unit Tests | Set up pytest, write unit tests | 6 | 2024-09-10 | 2024-09-15 | Learn testing methodologies, how to use pytest, and write tests for Flask applications. | Start with simple tests, ensure you understand the importance of testing, and practice writing unit tests.
2.2: Continuous Integration Setup | Set up CI pipeline with GitHub Actions | 4 | 2024-09-16 | 2024-09-19 | Learn about Continuous Integration (CI), setting up GitHub Actions, and automating tests. | Start with simple CI configurations, integrate testing into your pipeline, and understand the benefits of CI.
2.3: Docker Integration | Write Dockerfile, set up Docker Compose | 5 | 2024-09-20 | 2024-09-24 | Learn Docker basics, how to containerize a Flask app, and manage multiple containers with Docker Compose. | Practice writing Dockerfiles, understand Docker networking, and how to use Docker Compose effectively.
3.1: Define User Preferences | Collect input, design algorithm for scheduling | 4 | 2024-09-25 | 2024-09-28 | Understand user input processing, algorithm design principles, and basic scheduling algorithms. | Research scheduling algorithms, understand the trade-offs of different approaches, and design with scalability in mind.
3.2: Implement Schedule Generation | Develop and test scheduling algorithm | 8 | 2024-09-29 | 2024-10-06 | Learn how to implement algorithms in Flask, test edge cases, and ensure algorithm efficiency. | Start with a simple algorithm, optimize as needed, and focus on test coverage.
3.3: Generate Multiple Schedule Options | Modify algorithm to generate multiple options | 4 | 2024-10-07 | 2024-10-10 | Learn how to modify algorithms for variability and user choice, and how to present multiple options. | Ensure the algorithm is flexible, consider user experience when presenting options.
4.1: UI/UX Design | Enhance UI with CSS, ensure responsiveness | 4 | 2024-10-11 | 2024-10-14 | Learn CSS basics, responsive design principles, and how to enhance user interfaces. | Focus on making the interface intuitive, use CSS frameworks like Bootstrap for responsiveness.
4.2: Add Interactivity | Implement dynamic features, add JS | 4 | 2024-10-15 | 2024-10-18 | Learn JavaScript basics, how to interact with Flask back-end, and improve user interactions. | Start with simple JS enhancements, progressively add more complex interactivity.
5.1: Final Testing and Debugging | Thorough testing, bug fixing | 4 | 2024-10-19 | 2024-10-22 | Learn debugging techniques, final testing strategies, and how to ensure stability. | Test on different devices and browsers, focus on fixing critical bugs first.
5.2: Deployment to Production | Prepare and deploy application | 3 | 2024-10-23 | 2024-10-25 | Understand deployment processes, how to configure a production environment, and deployment tools. | Consider using platforms like Heroku, AWS, or DigitalOcean, ensure security and performance are prioritized.
5.3: Post-Project Enhancements | Add average calculation feature | 2 | 2024-10-26 | 2024-10-27 | Learn how to extend existing projects, add new features post-launch, and maintain code quality. | Ensure the new feature integrates smoothly with the existing code, and keep the codebase clean.